## Scheme
Lessons Learnt Log
Programme Name: Southwark Construction
Last updated: | Lauryn Morley | 2024-08-15
Project reference followed by number, e.g. PR_Act001 | A full description of the action |  |  |  | Update on progress | Select from drop down menu
Lessons Learnt ref | Date Identified | Lead | Adhoc area | Focus area / Theme | Detail | Comments and Recommendations
LL_0000 | 16.02.2024 | Georgie Hendriks | Project Monthly Review | Defects Management | Contractor being based 2 hours away from Southwark so additional time and costs for callouts. (GH - Ivychurch) | Lessons learnt identified at Monthly Programme Review meeting
LL_0001 | 16.02.2024 | Alex Talbott | Project Monthly Review | Decision Making | Early structural surveys will flag risks that may result in extra works, time and cost on a project - the TMO roof at Mary Datchelor is very weak. | Lessons learnt identified at Monthly Programme Review meeting
LL_0002 | 15.08.2024 | Georgie Hendriks | TAs 1, 2 and 3 | Design and Planning | Fireproofing and soundproofing were addressed later, which caused issues related to planning. Marie noted that the design lacked detail and recommended completing all planning with clear conditions before updating drawings and specifications. This approach, while potentially causing initial delays, could prevent numerous issues later. | Detailed initial surveys are ideal to reduce construction time, though collaboration can mitigate detail deficiencies.
LL_0003 | 15.08.2024 | Georgie Hendriks | TAs 1, 2 and 3 | Stakeholder Engagement | Niblock requested for Southwark's M&E team engagement but took 2-3 months before they said the did not have the capacity. This was a major failing. Although would have had cost implications Bailey Garner could have hired their own M&E team to review. A lack of Southwark’s input led to an overreliance on design, which resulted in issues later. | Better early involvement and timely questions are essential.
LL_0004 | 15.08.2024 | Georgie Hendriks | TAs 1, 2 and 3 | Cost Impact | Costs related to ASHPs extended beyond the units themselves, including scaffolding for pipework and changes in flooring. Feasibility studies should account for these costs and potential delays if design decisions are made late in the process.
LL_0005 | 15.08.2024 | Georgie Hendriks | TAs 1, 2 and 3 | Quality | While ER and specifications were generally good, some aspects needed adjustment. For example, doors from PremDors had a 57-week lead time, and industry standard products may not be suitable for older building refurbishments. Custom solutions may be necessary.
LL_0006 | 15.08.2024 | Georgie Hendriks | TAs 1, 2 and 3 | Handover | M&E issues delayed the handover. The detailed handover process, designed for new builds, was often not applicable. There were excessive inspections; a more streamlined approach with a snag and de-snag process would be more effective. Baily Garner’s continuous snagging and preemptive visits before being invited were noted as issues.
Note on B5: Morley, Lauryn: Date lessons learnt was identified
Note on C5: Morley, Lauryn: Lead of Project or Programme
Note on D5: Morley, Lauryn: This is for any other areas where the Lessons Learnt might have arose from e.g another department like Fire Saftey
Note on E5: Morley, Lauryn: If Focus area or theme is not there, please insert this manually
Note on F5: Morley, Lauryn: Detail of the lessons learnt

## Programme
Lessons Learnt Log
Programme Name: Southwark Construction
Contact: Lauryn Morley
Last updated: 17 June 2025 |  |  |  |  | Problem | What does it tell us? | How do we fix it?
Project reference followed by number, e.g. PR_LL001 |  |  |  |  | What went well, what didn't go so well or was lacking? | What effect did this have on your project? How did this present itself? | What would you recommend to ensure the success of future projects on the basis of your experience?
Lessons Learnt ref | Date Identified | Origin | Construction Period | Focus area / Theme | Challenge | Lesson | Recommendations | Owner | Implementation status
LL_0001 | 07.12.2022 | Susannah Oso | KM2 Stage | Decision Making | Decisions were not made about estate improvement works early enough in the project. This allowed scope creep, which resulted in additional costs and an overall increase in project and programme spend. | Estate improvement works should always be picked up as part of the main project scope. | Have a clear project brief and scope, and review design proposals at an early stage with design review panels. Monitor scope and proposed changes closely. Change control should be used for any changes to scope.
LL_0002 | 15.08.2024 | Georgie Hendriks | KM4 - KM5 Stage | M&E | The handover process was not followed correctly, meaning the M&E team were not on board at the correct stages, resulting in M&E issues delaying the handover. | The detailed handover process, designed for new builds, is key to ensuring that the correct stakeholders are involved at key points of project delivery. | The handover process, is to be followed throughout the lifecycle of the project. A more streamlined approach with a snag and de-snag process would be more effective.
LL_0003 | 15.08.2024 | Georgie Hendriks | KM2 - KM3 Stage | M&E | Contractors are requesting Southwark's M&E team engagement but the team do not always have the capacity to respond in a timely manner, resulting in cost implications and delaying the project. | Early engamanet with the councils M&E team are vital to ensure that they have capactity to responsed to contracotrs which will reduce in later complications. | Better early involvement and timely questions are essential. The EA could have hired their own M&E team to review.
LL_0004 | 08.06.2023 | Georgie Hendriks | KM2 - KM3 Stage | Decision Making | S278 works are not always included in tender documents, causing delays and additional costs. | If S278 works are not planned at the start of the contract it can cause delays and additional expediture, and potentially have a negative impact on working relationships between the counil and the contractor. | Ensure S278 works are included as part of the tender documents and are started early.
LL_0005 | 26.06.2023 | Georgie Hendriks | KM2 - KM3 Stage | Stakeholder Engagement | Internal stakeholders are not being engaged at the start of projects. The lack of engagment can lead to delays and increased costs. | Not engaging internal stakeholders at the appropriate times can cause significant project risk. Early involvement ensures that interal stakeholders are aware of any potential issues and expectations are aligned. | Engage with internal stakeholders as early as possible in the project lifecycle. Have early meetings with internal stakeholders and provide as much information to avoid any complications further down the line.
LL_0006 | 05.02.2024 | Nannette Sayki | KM2 Stage | Cost Impact | A large portion of additional project costs, particularly related to contamination and unforeseen ground conditions has resulted from relying on industry-standard site investigations conducted only after the start on site. This has led to increased costs and delays. | Completing a site investigation after start on site can increase the risk of finding unexpected site conditions, which then can increase costs and effect poject deadlines. Early site investigations and throughtout project cycle, is essential to mitigate any risks or cost implications. | Pre-tender site investigations on all sites. The new programme accounts for an enhanced approach to intrusive surveys that are being carried out to identify and mitigate site risk. This includes the instruction of phase two intrusive surveys.
LL_0007 | 05.02.2024 | Nannette Sayki | KM2 Stage | Stakeholder Engagement | Being tied into large-scale projects that become unaffordable after contract start. Once Southwark are commited into a single stage contract, the council are not able to respond to any unknown risks or budget issues, which could lead to paused projects. | A two-stage tender approach enables the council to withdraw from progressing to main works if necessary. This was utilised on Bells and Lindley and Sceaux Gardens which were recently paused due to budget pressures. | Two-stage tenders, which include a pre-construction services agreement (PSCA), should be used to enable Southwark and contractors to limit any site and design risks before entering into the main contract.
LL_0008 | 05.02.2024 | Nannette Sayki | KM4 - KM5 Stage | Cost Impact | The increase in build costs, inflation, enhanced building regulations and building safety requirements have led to project contingencies being exceeded. This has resulted in a high number of GW3 reports being requested for additional funds. | Contingencies are not always sufficient to cover cost increases throughout the lifecycle of some projects. Without financial planning, projects could risk of budget overrun and project delays to await for funding. | For future schemes, contingency of between 12% - 15% of the contract sum will be considered on a scheme-by-scheme basis to provide a more realistic cover for unforeseen events, thus reducing the need for a contract variation approval. This will also help to mitigate the risk of the council over-committing resources and borrowing capacity to the programme.Southwark Construction will continue to robustly monitor budget management and cash flow and project and programme level. Southwark PAMWIN is used to oversee project performance. Should it be identified that a large proportion of the contingency is required to be drawn, this will be flagged as part of the risk monitoring in the monthly project reviews.
LL_0009 | 16.07.2024 | Zoe Davies | KM4 - KM6 Stage | Cost Impact | Contractors (Guildmore) submitting multiple invoices, causing concerns around duplicate payments. Ths shows that there is reliance on contractors and EAs to manage the financial accuracy. | Relying on EAs and contractors with monitoring invoices and the councils finances can lead to duplication of payments. We need to be more robust in our project and budget management. | Trackers to be used to verify what has been paid so no duplicate payments are made and teams can keep a track of costs. These additional checks help create an extra layer of verification.
LL_0010 | 16.07.2024 | Zoe Davies | KM5 - KM6 Stage | Defects Management | Contractors (Guildmore) have been unresponsive and uncooprative in managing defects, this has led to delays and frustration with residents. | Not having any clear contractual obligations and time management in resolving defects results in uncertainty and no accountability regarding defects resolution which could result in councils reputational damange, additional costs and unresolved defects. | Contracts should clearly outline the defects management process and expected timelines for addressing defects, to avoid ambiguity and ensure accountability. Monitor contract performance during the defects period.
LL_0011 | 16.07.2024 | Zoe Davies | KM4 - KM6 Stage | Stakeholder Engagement | There has been a high turnover of staff, especially contract managers, this has flagged wider issues within the contractors organisation. | When people leave abruptly, it's rarely without a reason. Instead of dismissing these departures, there should have been a proactive effort to understand the motivations behind them. | For future contractors that have high turnover of staff, project managers to investigate the reason why this may be happening to get to the root of any issues.
LL_0012 | 15.04.2025 | Andrew Rogers | KM5 - KM6 Stage | Handover | New built homes are experiencing long void periods before being occupied. This has resulted in loss of income for the council. | Delays in allocating the new homes, this can have a financial impact. Pre-allocating homes before handover would allow the council to maximise rent and council tax income. It could also help us to ensure that disabled access properties have bespoke adaptations before handover. | Pre-allocation meetings to be undertaken to avoid having void properties for a long period of time for new builds. Implement a pre-allocation process for all new build homes, ideally at KM4 to KM5 of construction phase.
LL_0013 |  | Edyta Mikulo (Housing Supply Manager) | KM5 Stage | Programme | There have been recurring issues where newly built properties are created on Northgate with incorrect details (e.g. size, adaptations, floor level). | Accurate and up to date property information must be reflected in Northgate before the allocation process begins. Creating property records before receiving final building control approval can lead to inconsistency. | Project teams and managers should ensure that final, approved accommodation schedules are used to update Northgate records before properties are made available on Homesearch. A clear process to be implemented to verify and amend property details post building control approval, with defined responsibilities for updating the system.
LL_0014 |  | William Owen | KM5 Stage | Handover | Project handovers from other teams (e.g. Major Works) often are disorganised or have incompleted documentation, causing delays and confusion with missing or unclear information. | Lack of standard project information can lead to inefficiencies and errors. Ensuring that all relevant documentation is clearly organised and complete at the point of handover is essential for continuity and effective project delivery. | Introduce a standarised handover process by reqestion that other teams complete a Southwark Construction Handover form and adopt the Southwark Cnstrction file struture.
LL_0015 |  | William Owen | KM1 - KM6 Stage | Governance | Key governance documents (e.g. Gateway reports, Cabinet papers) sometimes lack clarity regarding the scope of recommendations, particularly around budget allocations and permissible spend. | If recommendations are unclear, especially about how flexible the funding is, it can be hard to follow through with strategic plans. When the spending limits don’t clearly match the report’s suggestions, it can cause delays in comleting certain activities e.g. community engagement. | Future reports and Cabinet papers should clearly state what each recommendation includes, especially regarding how the budget can be used. If flexibility is needed for example, for consultation or early engagement this should be clearly noted in both the narrative and financial sections.
Note on B6: Morley, Lauryn: Date lessons learnt was identified
Note on C6: Morley, Lauryn: Lead of Project or Programme
Note on E6: Morley, Lauryn: If Focus area or theme is not there, please insert this manually
Note on G6: Morley, Lauryn: Detail of the lessons learnt

## Theme areas
Decision Making
Programme
Quality
Cost Impact
Stakeholder Engagement
Coordination of Design
Design and Planning
Legal
Procurement
Resourcing
Governance
Development Agreements
Defects Management
Handover
Change Management
Key Milestones
Building Control
Heating system
Pamwin
M&E